## Project Planner
Echolocation - Project Planner
A Gantt Chart showing the development of the game Echolocation for IMAT1910 - Game Prototype Development |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS - IN DAYS - START DATE: 23/02/2020 - END DATE: 18/04/2020 - TOTAL DAYS: 55 DAYS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
Art - Shoe Design | 1 | 2 | 1 | 1 | 100%
Art - Enemy Design | 1 | 2 | 1 | 2 | 100%
Art - Bell Flower | 1 | 2 | 1 | 1 | 100%
Art - Font Type | 1 | 2 | 1 | 3 | 100%
Art - Logo | 1 | 2 | 1 | 1 | 100%
Art - All Other Art | 1 | 35 | 4 | 40 | 100%
Audio - Bell Flower | 1 | 2 | 2 | 1 | 100%
Audio - Footsteps (All) | 1 | 2 | 2 | 3 | 100%
Audio - Win/Lose Sound | 1 | 2 | 2 | 3 | 100%
Scripts - Moving the Player | 1 | 7 | 3 | 6 | 100%
Scripts - Line System | 1 | 7 | 4 | 15 | 100%
Scripts - Damage System | 1 | 7 | 4 | 3 | 100%
Scripts - Ground Types | 7 | 7 | 7 | 12 | 100%
Audio - Title Screen Music | 7 | 3 | 7 | 3 | 100%
Design - All Menus (Main and Options) | 7 | 7 | 7 | 15 | 100%
Scripts - Main Menu | 7 | 7 | 8 | 10 | 100%
Design - Credits | 7 | 7 | 7 | 5 | 100%
Scripts - Credits | 7 | 7 | 8 | 4 | 100%
Scripts - Stomp Mechanic | 14 | 7 | 16 | 5 | 100%
Scripts - Save System | 14 | 7 | 16 | 4 | 100%
Scripts - Bell Flower | 14 | 7 | 14 | 4 | 100%
Scripts - Pick Up System | 14 | 7 | 16 | 3 | 100%
Scripts - Win Condition | 21 | 7 | 21 | 3 | 100%
Scripts - Sound Manager | 21 | 7 | 21 | 3 | 100%
Scripts - Water | 21 | 7 | 21 | 9 | 100%
Art - Level Ideas | 21 | 14 | 21 | 14 | 100%
Design - Make Levels | 35 | 7 | 35 | 17 | 100%
Scripts - Enemy Movement System | 35 | 7 | 35 | 5 | 100%
Scripts - Hide In Playmode | 35 | 7 | 35 | 4 | 100%
Design - Pause Menu | 35 | 7 | 37 | 3 | 100%
Scripts - Pause Menu | 35 | 7 | 38 | 2 | 100%
Testing | 42 | 7 | 42 | 7 | 100%
Bug Fixes | 49 | 7 | 49 | 7 | 100%
Polish | 49 | 7 | 49 | 7 | 100%